## Summary
AM Daisy Requirement Analysis and Timelines
Executive tracker based on provided requirement/task list
Metric | Value | Status | Count
Total Tasks | 23 | Done | 3
Completed | 3 | Dev-Done | 2
Dev-Done | 2 | In-Progress | 1
Pending | 17 | Pending | 17
Complexity | Count | Dependency Snapshot | Count
High | 9 | Tasks With No Dependency | 4
Medium | 14 | Tasks With External Dependency | 19
Low | 0 | High Complexity Pending | 8

## Task Tracker
AM Daisy requirement analysis and timelines
Prepared: 2026-07-03
Task ID | Client Q# | Task Title & Description | Complexity | Key Dependencies | Status
TASK-01 | Q2 | Fuzzy Duplicate Matching: Cross-field matching via rapidfuzz / recordlinkage | High | None | Done
TASK-02 | Q3 | Multi-System Source Reconciliation: Aligning ERP/CRM schemas | High | Sample schemas | Pending
TASK-03 | Q4 | Hierarchy-Aware Matching: Parent-child relationship checks in validation | High | Parent-child schema definitions | Pending
TASK-04 | Q5 | Deterministic Golden Record Engine: Column-level merge priorities | High | Governance priority rules | Pending
TASK-05 | Q6 | Complex Fallbacks & Coalescing: Timestamp-based field merging templates | High | Fallback logic details | Pending
TASK-06 | Q7 | Interactive Staging Dashboard UI: Steward override panel in Next.js | Medium | Override API & DB schema | Pending
TASK-07 | Q11 | Draft/Approved Rule Workflows: Rules state machine in Prisma/FastAPI | Medium | None | Done
TASK-08 | Q12 | Centralized Audit Trails: Operation audit logging in PostgreSQL | Medium | None | Done
TASK-09 | Q15 | Pre-built ERP Connector Wrappers: SAP RFC/OData and Dynamics APIs | High | ERP Sandbox Credentials/APIs | Pending
TASK-10 | Q16 | FastAPI Ingestion Adapters: Batch adapters for enterprise pipelines | Medium | API documentation | Pending
TASK-11 | Q17 | HANA/SAP Staging Writebacks: Export drivers to SAP HANA staging tables | High | Staging table write credentials | Pending
TASK-12 | Q19 | SAP MDG Validation Translation: Parse and map MDG rule schemas to YAML | Medium | MDG rule schema samples | Pending
TASK-13 | Q20 | Orchestrated Sync Pipelines: Airflow/Prefect sync operators | Medium | Orchestrator deployment | Pending
TASK-14 | Q22 | Continuous Celery Processing Queue: Redis queue integration | High | Redis / Celery deployment | Pending
TASK-15 | Q23 | Real-Time Pre-Entry Validation: Low-latency check API middleware | Medium | CRM/ERP hook configuration | Pending
TASK-16 | Q24 | Celery Beat Automated Monitoring: Scheduled quality checks | Medium | Staging DB connections | Pending
TASK-17 | Q25 | Multi-Channel Notification Alerts: Slack, MS Teams, and Email webhooks | Medium | Webhook URL configurations | Dev-Done
TASK-18 | Q31 | Fine-Grained Role-Based Access Control: FastAPI/Prisma RBAC | Medium | Entra ID AD group maps | Pending
TASK-19 | Q32 | Microsoft Entra ID SSO: OpenID Connect auth in NextAuth.js | Medium | Entra ID App registration config | Pending
TASK-20 | Q33 | Encrypted Credentials Manager: AWS KMS / Azure Key Vault integration | Medium | Cloud KMS IAM permissions | Pending
TASK-21 | Q36 | Multi-LLM LiteLLM Router Integration: Dynamic route failover | Medium | LLM API keys & configurations | Dev-Done
TASK-22 | Q37 | Enterprise Production Helm Charts: Deployment & autoscaling (HPA) | High | EKS/AKS access | Pending
TASK-23 | - | Enhancing Accuracy Results: Merge accuracy result optimization and validation metrics | Medium | None | In-Progress

## Lookups
Status | Count | Complexity | Count
Done | 3 | High | 9
Dev-Done | 2 | Medium | 14
In-Progress | 1 | Low | 0
Pending | 17